Progress Rpt.

# Monthly

| Brand/Location: Home 2 Suites, 3386 E. Main St., Eagle Pass, TX 78852 |  |
| --- | --- |
| Hilton Project #.: 22-246ND |  |
| Report Date: 08/18/2026 | Construction Complete (%): 90% |
| Target Occupancy Date: 08/14/2026 (scheduled CO) | Target Opening Date: 08/25/2026 pending elevator updates |

Current Project Status:

- Cold-Formed Metal Framing – 100% complete.

- Light Gauge Metal Framing on 1st–4th floors – 100% complete.

- MEP’s

  - Electrical rough-in – All floors passed inspections.

  - Plumbing rough-in – All floors passed inspections.

  - Fire sprinkler – All floors passed inspection and hydro test.

  - Fire alarm – 100% complete with wiring; 1st floor trim out 100% complete.

  - Electrical finish – 4th floor 85% complete; 3rd floor 08/17/2026 – 08/18/2026; plumbing finish – 4th floor 08/17/2026 – 08/21/2026.

  - HVAC units set and installed – 100% complete; remaining ductwork trim ongoing.

  - Mechanical and electrical to remobilize for remaining trim-out in a single mobilization once staging guestrooms are cleared and exterior windows closed (targeted 08/19/2026).

- Exterior

  - Roof, waterproofing, and siding – 100% complete.

  - Masonry – 100% complete except capstones (fabricated; delivery being scheduled).

  - EFIS – remaining flash and install 50% complete; completion scheduled 08/25/2026.

  - Windows – closing of remaining exterior openings underway, targeted 08/19/2026; caulking 08/24/2026.

  - Underground electrical, light poles, and transformer – 100% complete.

- Dumpster Enclosure – 90% complete; roll-up door and lighting 08/21/2026 – 08/28/2026.

- Openings & Finishes

  - Interior door frames – 1st and 2nd floors 100% complete; frames and doors 3rd floor 08/17/2026 – 08/19/2026, 4th floor 08/20/2026 – 08/26/2026.

  - Gypcrete – 100% complete; corridor and stair-landing repairs begin 08/20/2026.

  - Insulation, drywall, tape & float, prime and paint – 100% complete all floors (drywall at elevator shaft walls to follow).

  - Ceramic flooring – 90% complete all floors.

Current Project Status (continued):

- Interior Finish-Out by Floor – 40% complete overall (per completion schedule dated 08/18/2026).

  - 1st floor – rooms 80% complete, common areas 55%; 2nd floor – rooms 39%, common areas 14%.

  - 3rd floor – rooms 33% complete, common areas 40%; 4th floor – rooms 37%, common areas 22%.

  - FF&E installation currently paused; 14 guestrooms remain.

- Elevators & Stairs

  - Elevator installation underway (TKE on site since 08/10/2026); approximately three weeks to completion, in line with the 08/25/2026 – 09/14/2026 schedule window.

  - State elevator inspection carried 09/16/2026 per completion schedule; shaft-wall build-out and drywall at elevator walls follow TKE completion (09/17/2026 – 09/18/2026).

  - Stair 1 and Stair 2 finish-out (landing repairs, paint, carpet, base) begins 08/20/2026.

- Site Work & Exterior Improvements

  - Concrete paving, flatwork, and pool deck and coping – 100% complete; entrance pour-back completed 08/14/2026, finish touch-up to follow.

  - Front retaining wall complete; headwall repair at entrance scheduled 08/19/2026.

  - Irrigation – 63% complete; landscaping (trees, plants, mulch) 75% complete, finishing by 08/28/2026; metal edging selection pending.

  - Pool – plaster completed 08/17/2026, fill underway; reported leak to be verified once full; equipment room 71% complete.

  - Ornamental iron pool fence installation begins 08/20/2026; temporary safety fencing in place.

Delay/Impact:

- Elevator installation is the critical-path item; per the Hilton 30-day report dated 07/24/2026, the 08/25/2026 target opening date remains, pending elevator updates.

- The state elevator inspection is called in by TKE once its work is complete (approximately three weeks out); historic lead times range from one to twelve weeks, and Triun is pursuing an early position in the inspection queue.

- Working-wall/casework misalignment at four guestrooms – added cabinetry in design with RKH; Rooms 116 and 118 await written Hilton direction before any furniture is modified.

- Substantial Completion currently projected 10/08/2026; the overall completion schedule, including final inspections, runs through 10/13/2026. (see Daily Logs for updates)

Safety:

- All Subcontractors must turn in a Tool Box Talk weekly every Monday morning at 8:00AM (CST) before going onsite.

Pay Approval from Bank:

- Current pay application under reconciliation.

Weather Days:

- No weather delay days recorded this reporting period (07/16/2026 – 08/18/2026).

Planned Activities Next Month:

- Interior

  - Clear staging guestrooms and close exterior windows (targeted 08/19/2026); mechanical and electrical complete remaining trim-out in a single mobilization.

  - 1st floor – corridor carpet & tile 08/19/2026 – 08/21/2026 with base, corner guards, and paint touch-up to follow; common-room finish-out continues through 09/16/2026.

  - 3rd and 4th floors – frames & doors, electrical and plumbing finish 08/17/2026 – 08/26/2026; Stair 1 and Stair 2 finish-out 08/20/2026 – 08/31/2026.

  - 2nd floor – remaining touch-up paint (90% complete) 09/16/2026 – 09/21/2026 per completion schedule.

  - FF&E installation of the remaining 14 guestrooms upon resumption.

- Exterior & Site

  - EFIS completion by 08/25/2026; masonry capstone installation upon delivery.

  - Complete pool fill; pool fence and gates installation from 08/20/2026 with new plaster protected during welding.

  - Outdoor amenity areas – firepits, pet relief stand, outdoor lounge, porte cochere and lighting, FRC planters – 08/17/2026 – 08/31/2026.

  - Headwall repair 08/19/2026; TxDOT railing at entrance 08/28/2026 – 08/31/2026 (fabricator quote expected 08/19/2026).

  - Landscaping – trees, plants and mulch through 08/28/2026; dumpster storage enclosure completion 08/21/2026 – 08/28/2026.

- Elevators & Inspections

  - TKE elevator installation to completion (through 09/14/2026); state inspection carried 09/16/2026; shaft-wall build-out to follow.

  - Fire Alarm Final and Mechanical Final inspections – 08/24/2026.

  - Pre-inspection punch list issued 08/17/2026; open items pending guestroom completion include flooring, fire alarm, and telephone.

  - Pre-opening deliverables to Hilton (Certificate of Occupancy, ADA Certificate Form, Pre-Opening Inspection Checklist with photographs); next Hilton site visit 7 – 10 days prior to projected opening; address Hilton 30-day report observation items.

| Figure 1 | Figure 2 |  |
| --- | --- | --- |
| Figure 3 | Figure 4 |  |
| Figure 5 | Figure 6 |  |
| Figure 7 | Figure 8 |  |
| Figure 9 | Figure 10 |  |
| Figure 11 |  | Figure 12 |
| Figure 13 |  | Figure 14 |  |
| Figure 15 |  | Figure 16 |  |
| Figure 17 |  | Figure 18 |  |
| Figure 19 |  | Figure 20 |  |
| Figure 21 |  | Figure 22 |  |
| Figure 23 |  | Figure 24 |  |